## Sheet1
Story Points Completed by member participation
ID | Sprint Goal | Sprint Number | User Story | Story Type | Tasks | Story Points | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
00018 | Graphics | 5 | As a <player>, I need to <have graphics> , because I want to <see what I'm doing>. | F (functional), T (technical) | Move sprite | 30 | 5 (Louis) | 5 (Louis) | 10 (Louis) | 10 (Louis) | -
[5 empty] | Command pallete | 10 | 5 (Jason) | - | 5 (Jason) | - | -
[5 empty] | Highlight command | 15 | 8 (Jason) | - | - | - | -
0015 | Multiple Levels | 5 | As a <player>, I need to <have levels become more complex> , because I want to <have an increasingly challenging game>. | F (functional), T (technical) | Place Obstacle in Playfield | 34 | 14 (Ryan) | 10 (Louis) | 10 (Louis) | - | -
[5 empty] | Temporary Obstacle Graphics | 5 | 5 (Louis) | - | - | - | -
[5 empty] | Set up Implementation of Blocking Player | 35 | - | - | 5 (Louis) | 15 (Louis) | 15 (Louis)
0009 | Victory | 5 | As a <player>, I need to <have a victory screen>, because I want to <know when I beat the game>. | F (functional), T (technical) | Initial Character Placement | 10 | 7 (Louis) | 3 (Louis) | - | - | -
[5 empty] | Temporary Character Graphics | 3 | 3 (Louis) | - | - | - | -
[5 empty] | Set Up Character Movement | 30 | - | 10 (Louis) | - | 20 (Louis) | -