## Sheet1
Story Points Completed by member participation
ID | Sprint Goal | Sprint Number | User Story | Story Type | Tasks | Story Points | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
00017 | Login Page | 2 | As a <player>, I need to <have a login> , because I want to <save my progress>. | F (functional), T (technical) | Sign Up | 20 | 3 (Felix) | 2 (Felix) | 10 (Felix) | 5 (Felix) | -
[5 empty] | General Account | 10 | 3 (Felix) | 7 (Felix) | - | - | -
[5 empty] | Educator Account | 10 | 3 (Felix) | 7 (Felix) | - | - | -
[5 empty] | Guest Button | 3 | 3 (Felix) | - | - | - | -
00019 | Main Menu | 2 | As a <player>, I need to <have a main menu>, because I want to <select different options>. | F (functional), T (technical) | Level Select Button | 20 | 3 (Jason) | - | - | - | -
[5 empty] | Tutorial Button | 10 | 3 (Jason) | 2 (Jason) | - | - | -
[5 empty] | Logout Button | 10 | 2 (Jason) | - | - | - | -
[5 empty] | Settings Button | 5 | 1 (Jason) |  | - | - | -