## Sheet1
Story Points Completed by member participation
ID | Sprint Goal | Sprint Number | User Story | Story Type | Tasks | Story Points | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
00019 | Main Menu | 3 | As a <player>, I need to <have a main menu>, because I want to <select different options>. | F (functional), T (technical) | Level Select Button | 17 | 17 (Jason) | - | - | - | -
[5 empty] | Tutorial Button | 5 | 5 (Jason) | - | - | - | -
[5 empty] | Logout Button | 8 | 8 (Jason) | - | - | - | -
[5 empty] | Settings Button | 4 | 4 (Jason) | - | - | - | -
00006 | Obstacle Object | 3 | As a <player>, I need to <have easily identifiable obstacles> , because I want <my goal to be clear>. | F (functional), T (technical) | Place Obstacle in Playfield | 34 | 14 (Ryan) | 10 (Louis) | 10 (Louis) | - | -
[5 empty] | Temporary Obstacle Graphics | 5 | 5 (Louis) | - | - | - | -
[5 empty] | Set up Implementation of Blocking Player | 35 | - | - | 5 (Louis) | 15 (Louis) | 15 (Louis)
00020 | Character Object Placeholder | 3 | As a <player>, I need to <have a character to control>, because I want to <be able to traverse the levels> | F (functional), T (technical) | Initial Character Placement | 10 | 7 (Louis) | 3 (Louis) | - | - | -
[5 empty] | Temporary Character Graphics | 3 | 3 (Louis) | - | - | - | -
[5 empty] | Set Up Character Movement | 30 | - | 10 (Louis) | - | 20 (Louis) | -